## Sheet1
Task ID | Task Name | Assigned To | Start Date | End Date | Status | Hours Worked | Planned Hours
1 | Initial Planning | John | 2024-09-01 | 2024-09-05 | Completed | 8 | 6
2 | Requirement Review | Sara | 2024-09-03 | 2024-09-10 | In Progress | 5 | 10
3 | Design Phase | Tim | 2024-09-05 | 2024-09-12 | Not Started | 0 | 12
4 | Development | Sara | 2024-09-10 | 2024-09-20 | Not Started | 0 | 15
5 | Testing | John | 2024-09-15 | 2024-09-25 | Not Started | 0 | 8